## Highlights & Low lights
Project Manager | Project | Month | Highlight | Lowlight
Joshua Samuel | Vertex | January | • Conducted a working session with DTE and Web Development teams to review and align on the Q1 2026 web updates roadmap, ensuring clear direction for | Awaiting the final signed SOW and PO
upcoming HCP and DTC initiatives
• Phase 2 Retrospective Campaign Taxonomy has been delivered on January 20th, 2026
Shreya Rao | Incyte | January | Received client communication on Qualtrics thereby creating an opportunity for having qualtrics functional | Awaiting signed SOW and PO
Drupal update go live on all 37 websites and we performed live QA with no major issues found
Accessibe go live on 8 unbranded sites
More opportunites to engage with the clients through 1:1 connects
Nataraj Selvaraj | Ipsen | January | Value added: Configuring Key Events for all Ipsen websites | NA
Prithvi Raj | Amgen | January | ​> Completed GA4 basic + custom tracking QA on DEV JP website https://dev.speakerslide.amgenpro.jp/ ​ | NA
> Completed GA4 basic + custom tracking QA on DEV DK website https://dev.mitkolesterol.dk/ ​
​> Successfully completed GA4 basic tracking setup on Live FR website https://www.amgen.fr/ ​
​> Delivered regular monthly and weekly reports for Japan (6 brands)​
https://evenity.jp, https://blincyto.jp, https://repatha.jp, https://lumakras.jp, https://aimovig.jp, https://otezla-japan.jp​
​> Fulfilled GA4 tracking setup on Cloud (Amgen landing page) pages. Example landing page:​>
https://cloud.amgeninfo.com/BR_Video_Dr_Carmelo​
https://cloud.amgeninfo.com/instructions_for_the_pre-filled_pen-video​
https://cloud.amgeninfo.com/cardiomedicalaffairs​
https://cloud.amgeninfo.com/immunoMIND​
https://cloud.amgeninfo.com/bfm_video_pt-BR​
> Fulfilled campaign tracking (UTM/Newsletter) requests for redamgen.com websites.
Prithvi Raj | Regeneron | January | > | NA
Nataraj Selvaraj | Calliditas | January | NA | NA
Nataraj Selvaraj | Soleno | January | NA | NA
Samanvey Gupta | GSK 3rd Party tagging | January | 1. Tag Implementation - 115 tags were implemented/re-implemented in January | NA
2. Tag Expiration Process: 6623 tags sent for 11 agency confirmations, 1747 to be retain and 4876 to be pause.
a. Among 1747, we have put active labels in tealium on 1380 tags till now
b. For 4876 tags to pause: CMI completed (912/1057), pulsepoint completed (10/10) and Aim (1/22) tags have been put on Pause and their QA is WIP
3. Tag Hawk:
a. Tool Development - Team is validating 500+ tags (either pausing the tags or fixing) for which data is not flowing to Tag Hawk and its WIP
b. Master Table - Started updated Master table also from 2021-2023 implemented tickets. (~4400 tags to update)
4. Cookie Consent - Continued working on the required fix for all 85 websites across 11 profiles, 9 profiles are completed
Vatsala Mishra | Gilead | January | 1. End of the year deck for 2025 presented to client | NA
2. Dashboard delivered for trodelvy DTP
3. Work started for migration of first site on EDS Kitemedinfo
4.2025 analytics report for careers pages
5. Go live of HIVclinicalinsights, where team worked on PST shift and delivered on time
6. OT exception work completed for gileadpro websites

## QBR
Account | PMs | Offshore Leads | Delivery Leads | Project Start date | QBR Start Date | QBR Delivery Type | Comments | December | January | February | March | April | May | June | July | August | September | October | November | December
Abbvie | Joshua | Pooja, Joshua | Harish, Anshul | 2023-01-01 | 2023-01-01 | Independently | Follows Jan-Dec(FY)
Amgen | Prithvi | [5 empty] | Follows Jan-Dec(FY). Currently in talks Planning to happen in next Quarter.
AZ | Abrar/Vatsala | NA | Bonnie Sananda | 2022-09-01 | 2023-01-01 | In Collaboration | Indegene present Monthly, Quaterly, Half yearly and annual decks to AZ. 2022 was presented as an Annual Business Review to client and as QBR to Sharan. 2023 Q1 and Q2 was delivered together as H1 review.
In Q3, it was delivered as EOY 2023. In Q4 2024, it'll be delivered as quaterly OGR
Bayer | Jinan |  |  |  |  | In Collaboration
Fresenius | Joshua | Malhar, Joshua | Malhar, Anshul | 2023-01-01 | 2023-01-01 | Independently | Follows Jan-Dec(FY).
2022 was presented as an Annual Business Review and 2023 Q1 and Q2 was delivered together 2023 Q3 and Q4 was delivered together
Genmab | Rashmi | [5 empty] | A collaborative QBR prepared in 2024 along with OT and SFMC teams and presented by Janice in May 2024
GSK | Jinan | [5 empty] | Q3 completed.
Incyte | Shreya | Shreya, Avishek, Apurv, Mohit | Anshul | 2023-01-01 |  | In Collaboration | QBR occurred till mid last year, after that Client requested for separate connect with smaller group (attendees : Heidi, Jay Khan and Incyte team) | NA | NA
This year no visibility yet.
but it was very focussed revolving around key topics and with limited folks. we had slides from our area and it was covered by Debashsish from campaign team
Ipsen | Nataraj | Rohan, Vikas, Anmol | Rohan & Anmol | 2023-01-01 | 2023-10-01 | In Collaboration | 1. Clients were on holiday in Q4,2023. | 2025-12-12
[7 empty] | 2. Q1,2024, internal discussions going on to see what can be presented to client. | The QBR held this month went well with positive feedback and no issues raised on deliverables. The client’s expectation is to increasingly engage from a strategic and consulting perspective.
3. Project progress/completion status, blockages gets discussed on weekly basis with client stakeholders.(Analytics and Dev)
Novartis | Kunal | [5 empty] | QBR planned in March
Regeneron | Prithvi | Avishek, Rajesh |  |  |  |  | Follows Jan-Dec(FY). QBR planning in progress for Q1. Likely to happen in Q2 .
Takeda | Himanshu | Nandita , Rashprit | Nandita Prasad and Arun Kumar | 2022-07-01 |  | In Collaboration | Indegene present Monthly, Quaterly, Half yearly and annual decks to Takeda.
Eisai | Nataraj | [5 empty] | New project, in initial phase
Beigene | [6 empty] | No QBR Planned
Calliditas | Nataraj | [5 empty] | QBR planned in March
Gilead | Vatsala | Surbhi | Surbhi,Namrata | 2025-01-01 | NA |  | We do have monthly operational review in place
Next QBR will be in collaboration with CPC team

## FTE
| 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
| Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground | Total FTE on ground
Abbvie | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Amgen | 2025-10-01: 2; 2025-11-01: 2; 2025-12-01: 2
AZ
Bayer
Fresenius | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
AZ tealium
GenMab
GSK
GSK 3rd party tagging
Incyte
Incyte Web studio | 2025-10-01: 3.5; 2025-11-01: 3.5; 2025-12-01: 3.5; 2026-01-01: 3.5
Ipsen | 2025-10-01: 1.25; 2025-11-01: 1.25; 2025-12-01: 1.25; 2026-01-01: 1.25; 2026-02-01: 1.25; 2026-03-01: 1.25; 2026-04-01: 1.25; 2026-05-01: 1.25; 2026-06-01: 1.25
Novartis
Regeneron | 2025-10-01: 8.75; 2025-11-01: 8.75; 2025-12-01: 8.75
Takeda | 2025-10-01: 8.5
EASAI
Alnylam
Vertex | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5

## Risks and Mitigation
Month | Week | Project Manager | Project | Risks | Owner | Root cause | Mitigation Steps | Impact | Status
January | Week 1 and 2 | Shreya Rao | Incyte | Movement of One trust and addition of new resource in between the deliverables |  | Team alignemnet changes | Planning for smooth KT with the new resource till they can handle tasks independently | Loss of Revenue for the BU | Ongoing
January | Week 1 and 2 | Prithvi Raj | Amgen | No Risk
January | Week 1 and 2 | Prithvi Raj | Regeneron | No Risk
January | Week 1 and 2 | Shobika | GSK | No Risk
January | Week 1 and 2 | Andrew | Allergan | No Risk
January | Week 1 and 2 | Andrew | Fresenius | No Risk
January | Week 1 and 2 | Vatsala Mishra | Gilead | No Risk
January | Week 3 and 4 | Vatsala Mishra | Gilead | No Risk
January | Week 1 and 2 | Joshua Samuel | Vertex | No Risk
January | Week 3 and 4 | Joshua Samuel | Vertex | No Risk
January | Week 3 | Samanvey Gupta | GSK 3rd Party tagging | Cookie Consent Compliance - 85 websites across 11 profiles (6000+ tags) | GSK 3rd party tagging team | 3rd party Tags firing before accepting cookies | Completed required fix for 8 profile websites, Need to work for pending 3 profiles websites (Need ~3 hours/profile) | Legal compliance issues can be raised | In Progress
January | Week 3 | Andrew | Allergan | No Risk
January | Week 3 | Andrew | Fresenius | No Risk
January | Week 3 | Vatsala Mishra | Gilead | No Risk
January | Week 3 and 4 | Shobika | GSK | Use of outdated iPhone models for QA | Indegene | We are encountering challenges in mobile QA because the currently available iPhone devices are outdated, causing several UI elements and functionalities to either not display correctly or fail to function as intended. | 1. Replace the current outdated iPhone devices with a more recent iPhone model to ensure compatibility with latest OS versions and to support reliable, thorough mobile QA.
2. Until new model iphones are received, QA team is granted access with Browser Stack to perform Mobile QA
January | Week 3 and 4 | Joshua Samuel | Vertex | No Risk
January | Week 4 | Samanvey Gupta | GSK 3rd Party tagging | 1. Cookie Consent Compliance - 85 websites across 11 profiles (6000+ tags) | 1. Indegene working team | 1. 3rd party Tags firing before accepting cookies | 1. Completed required fix for 9 profile websites, Need to work for pending 2 profiles websites (Need ~3 hours/profile) | 1. Legal compliance issues can be raised | In Progress
|  |  |  | 2. Atul GSK and Tealium access pending | 2. GSK | 2. Access pending from GSK | 2. Om is working as backup but for few hours only | 2. Delay in deliverables
January | Week 4 | Andrew | Allergan | No Risk
January | Week 4 | Andrew | Fresenius | No Risk
January | Week 4 | Shreya Rao | Incyte | No Risk
January | Week 5 | Samanvey Gupta | GSK 3rd Party tagging | Week 4 Issues: Deliverables delayed. From 16th Jan, only bhola worked as implementation engineer as we didn't receive Atul tealium access. Team lost 36 hours of development work (considering 6 working days with ~6hrs/day capacity for 1 engineer). Bhola also had leave on 22nd Jan, so zero development happened on the project on 22nd Jan | 1. Indegene working team | 1. 3rd party Tags firing before accepting cookies | 1. Completed required fix for 9 profile websites, Need to work for pending 2 profiles websites (Need ~3 hours/profile) but don't have bandwidth to do this | 1. Legal compliance issues can be raised | In Progress
|  |  |  | Week 5 Risks: | 2. GSK | 2. Tealium Access pending from GSK | 2. Om is working as backup but for ~2 hrs and 1 or 2 days in a week | 2. Delay in deliverables this week also and low productivity
1. Cookie Consent Compliance - 85 websites across 11 profiles (6000+ tags)
2. Atul Tealium access pending, so we might lost development time this week also. Also, if bhola takes any urgent leaves this week also, so no development would happen on that particular days
January | Week 5 | Andrew | Allergan | No Risk
January | Week 5 | Andrew | Fresenius | No Risk
February | Week 1 | Andrew | Allergan | No Risk
February | Week 1 | Andrew | Fresenius | No Risk
January | Week 1 and 2 | Nataraj Selvaraj | Ipsen | No Risk
January | Week 3 and 4 | Nataraj Selvaraj | Ipsen | No Risk
January | Week 1 and 2 | Nataraj Selvaraj | Soleno | No Risk
January | Week 3 and 4 | Nataraj Selvaraj | Soleno | No Risk
January | Week 1 and 2 | Nataraj Selvaraj | Calliditas | No Risk
January | Week 3 and 4 | Nataraj Selvaraj | Calliditas | No Risk
February | Week 1 | Samanvey Gupta | GSK 3rd Party tagging | Jan Week 5 Issues: Atul still didn't receive Tealium PROD publish access. | 1. Indegene working team | 1. 3rd party Tags firing before accepting cookies | 1. Completed required fix for 9 profile websites, Need to work for pending 2 profiles websites (Need ~3 hours/profile) but don't have bandwidth to do this | 1. Legal compliance issues can be raised | In Progress
|  |  |  | Feb Week 1 Risks: | 2. GSK | 2. Tealium PROD Access pending from GSK | 2. Bhola (2nd developer on project) to do all the deployment | 2. Delay in deliverables this week also and low productivity
|  |  |  | 1. Cookie Consent Compliance - 85 websites across 11 profiles (6000+ tags) | 3. Indegene DE operations team | 3. Supporting other projects while 100% billable on gsk 3rd party project | 3. Need to support only gsk 3rd party project to expedite the KT process and cover backlog of more than 2500 tags | 3. Delay in deliverables
2. Atul Tealium PROD access pending
3. Atul is supporting other projects which might delay our project deliverables
February | Week 1 | Vatsala Mishra | Gilead | no Risk
February | Week 1 and 2 | Joshua Samuel | Vertex | No Risk

## Audits
Month | Project Manager | Project | Audit details | Details | Audit Closure Date
January | Sanket Agrawal | Takeda
January | Shreya Rao | Incyte | Performed PII audit on MPN connect | NO PII data recorded | 2026-01-24